## Sheet1
Project Name | Tenants Association Administration
Name | Task/Feature | Estimated Duration
Week1
Marcu Andrei | Invoices user front + back | 7 zile
Tolgoi Dragos | Register page front + back | 7 zile
Calina Florin | Dashboard administrator front + back | 7 zile
Matei Alexandru | Login page frontend, navbar | 7 zile
Week2
Marcu Andrei | Login front + back, routing, logout + login protection | 7 zile
Tolgoi Dragos | Navbar+Polls user+Polls admin+Dashboard User | 7 zile
Your account user
Your account administrator
Invoices admin
Services user
Services admin